## Slide 1
PERFORMED BY:
Kayla Canfield
GILEAD
Proposal
MEDUC 631-2 Capstone Grant Proposal | Mount St. Mary's University
SUPERVISED BY:
Professor Doug

## Slide 2
Program Purpose
Scaffolded writing instruction within existing coursework
GILEAD
The Academic Literacy Collaborative
The proposed Academic Literacy Collaborative will design and implement Gilead, a digital learning platform that delivers scaffolded writing instruction within first-year and lower-division undergraduate courses to improve student writing development and academic readiness.
120
Pilot Students
6
Course Sections
3
LMS Platforms
(Canvas, Moodle, Blackboard)
2
Pilot Semesters
(Oct 2026 – Jun 2027)
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
2 / 9

## Slide 3
Three Program Goals
What the Gilead pilot will accomplish
GILEAD
GOAL 1
1
Strengthen Writing Proficiency
Deliver structured, process-based writing instruction within existing first-year and lower-division coursework.
GOAL 2
2
Support Academic Integrity
Give instructors verifiable documentation of how students develop their writing over time.
GOAL 3
3
Expand Equitable Access
Reach first-generation and underserved students within the LMS environments they already use.
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
3 / 9

## Slide 4
Goal 1: Strengthen Writing Proficiency
ISTE Std. 6 | CWPA/NCTE/NWP Framework | WAC Framework
GILEAD
Objective 1.1
Design and develop 8 scaffolded writing modules for Canvas, Moodle, and Blackboard.
ASSOCIATED TASKS
1
Develop instructional storyboards for all 8 Gilead modules; specify objectives, activities, and feedback prompts for each writing stage. (Instructional Designer; 6 weeks)
2
Build and test all 8 modules in Canvas with structured feedback from a 5-member faculty review panel before fall launch. (Platform Developer + ID; 4 weeks)
Objective 1.2
Implement Gilead modules across 6 lower-division course sections during the pilot year.
ASSOCIATED TASKS
1
Facilitate two 3-hour faculty PD sessions for 6 pilot instructors on platform navigation, module assignment, and progress monitoring. (Program Coordinator; late Aug 2026)
2
Administer pre- and post-semester writing assessments to all 120 students using a shared analytic rubric. (Program Evaluator; both pilot semesters)
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
4 / 9

## Slide 5
Goal 2: Support Academic Integrity
ISTE Std. 6 | CWPA/NCTE/NWP Framework
GILEAD
Objective 2.1
Configure process-documentation tools across all 6 pilot course sections.
ASSOCIATED TASKS
1
Program keystroke logging, draft-progression tracking, and time-on-task recording within Gilead before fall semester. (Platform Developer; 3 weeks)
2
Train 6 pilot instructors to read and interpret Gilead process records and AI-anomaly flags through a 2-hour workshop. (Program Coordinator; late Aug 2026)
Objective 2.2
Develop and distribute an academic integrity protocol for Gilead-generated process data.
ASSOCIATED TASKS
1
Draft the protocol in consultation with the Dean of Students and the academic integrity officer. (Principal Investigator; 4 weeks, Sep–Oct 2026)
2
Present the protocol at Faculty Senate and distribute to all pilot department chairs before spring 2027. (Program Coordinator; Nov 2026)
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
5 / 9

## Slide 6
Goal 3: Expand Equitable Access
ISTE Std. 6 | Culturally Sustaining Pedagogy (Paris, 2012)
GILEAD
Objective 3.1
Recruit a pilot cohort with at least 40% first-generation enrollment across all 6 sections.
ASSOCIATED TASKS
1
Coordinate with Institutional Research and First-Generation Student Success to verify enrollment thresholds; flag sections below threshold for outreach. (Program Coordinator; 2 weeks)
2
Administer baseline survey to 120 students on writing experience, comfort, and resource familiarity, stratified by first-generation status. (Program Evaluator; Week 1, Oct 2026)
Objective 3.2
Evaluate access and engagement outcomes at the close of each pilot semester.
ASSOCIATED TASKS
1
Analyze Gilead engagement data by first-generation status, Pell eligibility, and major; identify completion and proficiency disparities. (Program Evaluator; 2 weeks each semester)
2
Compile and submit equity reports with engagement patterns, proficiency gains, and recommended adjustments. (Program Evaluator; 3 weeks each cycle)
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
6 / 9

## Slide 7
Evaluation Plan
Mixed-methods, triangulated across all three goals
GILEAD
SURVEYS
Oct 2026, Dec 2026, Jun 2027
PARTICIPANTS
All 120 pilot students
DESIGN
Likert items on writing confidence, process familiarity, platform engagement, and access; mid-semester instructor survey on functionality.
INSTRUCTOR INTERVIEWS
Nov 2026 & Apr 2027
PARTICIPANTS
All 6 pilot instructors
DESIGN
Semi-structured 45-minute interviews on student engagement, process-record use, and platform refinement; thematic coding via codebook.
FOCUS GROUPS
Dec 2026 & Jun 2027
PARTICIPANTS
8–10 students × 2 cohorts per semester (stratified by first-gen status)
DESIGN
60-minute facilitated sessions on motivation, perceived access, and the experience of staged writing.
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
7 / 9

## Slide 8
Self-Care Plan
Sustaining quality engagement across the pilot year
GILEAD
Reflective Journaling
20 min / week
Each team member maintains a private professional journal documenting observations, decisions, and challenges across all four phases.
Quarterly Check-Ins
90 min / quarter
Facilitated team meeting at the close of each phase to surface concerns, share progress, and acknowledge contributions.
Movement Breaks
Two 20-min walks / week
Scheduled walking breaks during Phase 1 (development) and Phase 3 (full implementation) to support cognitive renewal.
Professional Reading
1 article / semester
Each team member selects an article in their program area, then shares a brief summary at the quarterly check-in.
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
8 / 9

## Slide 9
Program Budget
Total project cost: $75,920
GILEAD
By Goal
Goal 1: Strengthen Writing Proficiency
$30,900
Goal 2: Support Academic Integrity
$16,200
Goal 3: Expand Equitable Access
$11,300
TOTAL PROJECT COST
$75,920
Total Direct Cost (Goals 1–3)
$58,400
Evaluation Cost (10%)
$5,840
Indirect Cost (20%)
$11,680
THE ACADEMIC LITERACY COLLABORATIVE | Gilead Pilot
9 / 9