## 📋 About This Sample
Sigma Tau Delta Induction Cycle — Project Management Portfolio Sample
Kayla Canfield ¦ Administrative Assistant II ¦ Higher Education Administration
⚠ PRIVACY NOTICE: All student names, email addresses, GPA values, and academic records in this workbook are entirely fictional and created for portfolio demonstration purposes. This sample does not contain or represent any real student data. No FERPA-protected information appears anywhere in this workbook.
WHAT THIS WORKBOOK DEMONSTRATES
Multi-tab data architecture | Five interconnected tabs mirror a real project management system: eligibility tracking, event planning, communications, and outcomes — all in one workbook.
Cognitive load theory applied | Color coding, freeze panes, section headers, and alternating row fills reduce visual scanning time. Each tab has one job and one visual hierarchy.
FERPA-compliant data handling | The real workbook this sample is based on required careful separation of identifiable student records from planning materials. This sample demonstrates the system design without exposing any protected data.
Project lifecycle documentation | The planning checklist tab captures all six phases of the induction cycle with owners, due dates, and completion tracking — a handoff-ready document.
Data analysis for decision-making | The eligibility tracker shows how raw registrar data becomes an actionable shortlist, with member status checks, graduation year groupings, and eligibility rationale all surfaced at a glance.
Event coordination at scale | The communications log and event summary tabs reflect real coordination across students, faculty, and a national organization — three stakeholder groups managed simultaneously.
TAB GUIDE
📚 Eligibility Tracker | Fictional student roster showing eligibility analysis by program category and graduation year. Demonstrates data organization, GPA filtering logic, and member status cross-referencing.
✅ Planning Checklist | Full six-phase project checklist with task owners, due dates, priority levels, and completion status. Demonstrates project lifecycle management and documentation.
📅 Project Timeline | Week-by-week Gantt-style view of the 8-week induction cycle. Demonstrates timeline planning and phase sequencing.
📧 Communications Log | Outreach tracking for all eligible students across four touchpoints. Demonstrates stakeholder communication management and follow-up systems.
📊 Outcomes Summary | Post-event metrics, RSVP results, payment tracking summary, and process notes for future coordinators. Demonstrates outcome documentation and knowledge transfer.
SKILLS THIS WORKBOOK SURFACES FOR HIRING MANAGERS
Project Management
✦ Full lifecycle management
✦ Phase sequencing
✦ Deadline tracking
✦ Stakeholder coordination
✦ Risk documentation
✦ Handoff documentation
Data Analysis
✦ Multi-source data reconciliation
✦ Eligibility logic design
✦ GPA filtering
✦ Member database management
✦ Cross-tab accuracy verification
✦ Outcome measurement
Event Coordination
✦ Multi-stakeholder RSVP tracking
✦ Venue and logistics coordination
✦ Payment reconciliation
✦ Faculty coordination
✦ National org compliance
✦ Day-of execution
Design & Content
✦ Cognitive load theory applied
✦ Color-coded information hierarchy
✦ Typography consistency
✦ Multi-format deliverables
✦ Brand alignment
✦ FERPA-compliant materials
Communication
✦ Formal invitation drafting
✦ Multi-touchpoint outreach
✦ Faculty advisor liaison
✦ National organization reporting
✦ Student communication
✦ Post-event documentation

## 📚 Eligibility Tracker
Student Eligibility Tracker ¦ Spring 2026 ¦ Sigma Tau Delta Alpha Phi Iota
⚠ SAMPLE DATA — All names and records below are fictional, created for portfolio demonstration. No real student information is represented.
Eligibility Criteria: 3.0+ career GPA · 3.0+ English GPA · English major/minor · Sophomore standing or above · ≥3 completed Mount English courses
Last Name | First Name | Email (Sample) | Class Year | Grad Year | Career GPA | English GPA | Major(s) | Minor(s) | STD Eligible? | STD Member? | Category
ENGLISH MAJORS (7 students)
Ashworth | Morgan | m.ashworth@university.edu | SR | 2026 | 3.82 | 3.9 | English | Comm. Studies | Y |  | English Major
Blackwood | Riley | r.blackwood@university.edu | SR | 2026 | 3.91 | 3.95 | English | Philosophy | Y | ✓ Member | English Major
Thornton | Casey | c.thornton@university.edu | SR | 2026 | 3.42 | 3.38 | English | Creative Writing | N |  | English Major
Merriweather | Quinn | q.merriweather@university.edu | JR | 2027 | 3.74 | 3.68 | English |  | Y |  | English Major
Coldwell | Sam | s.coldwell@university.edu | JR | 2027 | 3.71 | 3.55 | English | History | Y |  | English Major
Westbrook | Bailey | b.westbrook@university.edu | SO | 2028 | 3.55 | 3.6 | English | Comm. Studies | Y |  | English Major
Whitmore | Alex | a.whitmore@university.edu | FR | 2029 | 3.68 | 3.72 | English |  | N |  | English Major
ENGLISH EDUCATION MAJORS (3 students)
Pemberton | Taylor | t.pemberton@university.edu | SR | 2026 | 3.74 | 3.8 | English | Sec. Ed. Cert. | Y | ✓ Member | English Education
Ravenswood | Jordan | j.ravenswood@university.edu | JR | 2027 | 3.6 | 3.55 | English | Sec. Ed. Cert. | Y |  | English Education
Ashbridge | Parker | p.ashbridge@university.edu | SO | 2028 | 3.88 | 3.91 | English | Sec. Ed. Cert. | Y |  | English Education
ENGLISH DOUBLE MAJORS (3 students)
Ellsworth | Jamie | j.ellsworth@university.edu | SR | 2026 | 3.65 | 3.7 | English + History |  | Y | ✓ Member | Double Major
Fairmont | Drew | d.fairmont@university.edu | JR | 2027 | 3.8 | 3.75 | English + Comm. |  | Y |  | Double Major
Hartwell | Morgan | m.hartwell@university.edu | SO | 2028 | 3.52 | 3.48 | English + Psych. |  | Y |  | Double Major
ENGLISH MINORS (4 students)
Cromwell | Spencer | s.cromwell@university.edu | SR | 2026 | 3.78 | 3.65 | Communications | English Minor | Y |  | English Minor
Lakeshore | Avery | a.lakeshore@university.edu | JR | 2027 | 3.44 | 3.5 | Biology | English Minor | Y |  | English Minor
Nightingale | Sage | s.nightingale@university.edu | SO | 2028 | 3.9 | 3.85 | History | English Minor | Y |  | English Minor
Thornfield | River | r.thornfield@university.edu | FR | 2029 | 2.85 | 2.9 | Psychology | English Minor | N |  | English Minor
■ Light Gold Row = STD Eligible, Not Yet a Member
■ Light Sage Row = Existing STD Member
■ Blush / Off-White = Standard alternating rows
Total Students: 17 |  |  | Eligible (Y): 14 |  |  | Existing Members: 3 |  |  | New Eligible (non-members): 11

## ✅ Planning Checklist
Sigma Tau Delta Induction Cycle ¦ Project Planning Checklist ¦ Spring 2026
6-Phase Project Cycle · Status: ✓ Complete ¦ ⏳ In Progress ¦ ○ Not Started ¦ ⚠ Needs Attention
Task | Owner | Due (Week) | Priority | Status | Notes | Deliverable
PHASE 1 — Data Pull & Architecture (Weeks 1–2)
Pull spring enrollment report from registrar | Admin Coord. | Week 1 | HIGH | ✓ Complete | Pull all English-connected students (majors, ed majors, double, minors) | Registrar report
Build multi-tab Excel tracking workbook | Admin Coord. | Week 1 | HIGH | ✓ Complete | Organize by program category; apply CLT design principles | Tracker workbook
Cross-reference enrollment against member database | Admin Coord. | Week 2 | HIGH | ✓ Complete | Flag existing members; remove graduated students from active pool | Updated member list
Identify eligible students (GPA + standing criteria) | Admin Coord. | Week 2 | HIGH | ✓ Complete | Apply eligibility criteria: 3.0+ GPA, sophomore+, 3+ ENGL courses | Eligibility shortlist
Submit eligibility list to faculty advisor for review | Admin Coord. | Week 2 | HIGH | ✓ Complete | Faculty advisor confirms or adjusts the list before outreach begins | Approved shortlist
PHASE 2 — Student Outreach (Weeks 2–3)
Draft induction invitation letter | Admin Coord. | Week 2 | HIGH | ✓ Complete | Formal invitation explaining STD, eligibility, and next steps | Invitation draft
Faculty advisor approves invitation language | Faculty Adv. | Week 3 | HIGH | ✓ Complete | Confirm language aligns with chapter standards | Approved draft
Send invitations to all eligible students | Admin Coord. | Week 3 | HIGH | ✓ Complete | Send via institutional email; log send date in communications tracker | Outreach log
Track RSVPs and payment confirmations | Admin Coord. | Week 3 | MED | ✓ Complete | Update comms log daily during RSVP window | RSVP tracker
Follow up with non-responding eligible students | Admin Coord. | Week 4 | MED | ✓ Complete | Second touchpoint sent 5 days after initial invitation | Follow-up log
Confirm dietary/accessibility needs for dinner | Admin Coord. | Week 4 | MED | ✓ Complete | Collect during RSVP process; share with venue coordinator | Needs list
PHASE 3 — Event Materials Production (Weeks 3–5)
Design and produce formal induction invitations | Admin Coord. | Week 3 | HIGH | ✓ Complete | HTML + print-ready format; MSMU branding; dark academia aesthetic | Invitation files
Create ceremony program | Admin Coord. | Week 4 | HIGH | ✓ Complete | Include member names, chapter history, faculty sponsors, national info | Ceremony program
Build honors dinner RSVP and seating materials | Admin Coord. | Week 4 | MED | ✓ Complete | Seat cards, table assignments, faculty RSVP confirmations | Dinner materials
Produce payment tracking log | Admin Coord. | Week 4 | HIGH | ✓ Complete | Record payment date, method, and confirmation for each inductee | Payment log
Prepare national organization enrollment forms | Admin Coord. | Week 5 | HIGH | ✓ Complete | Compile all required data fields; verify against member portal | Enrollment docs
PHASE 4 — Logistics & Coordination (Weeks 4–5)
Confirm venue and catering with campus events office | Admin Coord. | Week 4 | HIGH | ✓ Complete | Room booking, AV setup, catering order for expected headcount | Venue confirmation
Coordinate faculty sponsor attendance | Admin Coord. | Week 4 | MED | ✓ Complete | Collect RSVPs from faculty; send calendar invitations | Faculty RSVP list
Prepare day-of logistics checklist | Admin Coord. | Week 5 | MED | ✓ Complete | Arrival order, materials checklist, contingency plan | Day-of checklist
Confirm final headcount with venue | Admin Coord. | Week 5 | HIGH | ✓ Complete | Submit 48-hour headcount to catering | Final count
PHASE 5 — Induction Ceremony Execution (Week 5)
Set up ceremony space | Admin Coord. | Day of | HIGH | ✓ Complete | Arrange programs, place cards, materials at each seat
Manage check-in and payment collection at door | Admin Coord. | Day of | HIGH | ✓ Complete | Verify against RSVP list; collect any remaining fees
Coordinate ceremony proceedings with faculty advisor | Admin Coord. | Day of | HIGH | ✓ Complete | Run-of-show coordination; timing of oath, recognition, dinner
Photograph ceremony for departmental records | Admin Coord. | Day of | MED | ✓ Complete | Candid and formal photos for chapter records and dept. communications | Photo archive
PHASE 6 — Post-Event Documentation (Weeks 6–8)
Submit new member enrollments to national STD org. | Admin Coord. | Week 6 | HIGH | ✓ Complete | Enter payment confirmations, grad year, contact info into portal | Enrollment submission
Update master member database | Admin Coord. | Week 6 | HIGH | ✓ Complete | Add all newly inducted members; update graduation years for returning | Updated database
Reconcile payment records | Admin Coord. | Week 6 | HIGH | ✓ Complete | Match collected fees to enrollment list; flag any discrepancies | Payment reconciliation
Draft post-event summary for faculty advisor | Admin Coord. | Week 7 | MED | ✓ Complete | Headcount, inductees, financials, process notes, recommendations | Summary report
Archive all event materials per FERPA protocols | Admin Coord. | Week 7 | HIGH | ✓ Complete | File student records per institutional data retention policy | Archived files
Document process improvements for next cycle | Admin Coord. | Week 8 | MED | ✓ Complete | Note pain points, process changes, and handoff instructions | Process notes
Update tracking workbook template for next year | Admin Coord. | Week 8 | LOW | ✓ Complete | Refine tab structure based on this cycle's experience | Updated template
Total Tasks: 31 ¦ Phases: 6 ¦ Completed: 31 of 31 ¦ Status: PROJECT CLOSED

## 📅 Project Timeline
Sigma Tau Delta Induction Cycle ¦ 8-Week Project Timeline ¦ Spring 2026
█ = Active work period ★ = Key milestone/deadline Coord. = Admin Coordinator Fac. = Faculty Advisor
Phase / Task | Owner | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
PHASE 1 — Data & Architecture
Pull registrar enrollment report | Coord. | ★
Build Excel tracking workbook | Coord. | █ | █
Cross-reference member database | Coord. |  | █
Identify eligible students | Coord. |  | ★
Submit list to faculty for approval | Coord. |  | ★
PHASE 2 — Student Outreach
Draft invitation letter | Coord. |  | █ | █
Faculty advisor approves invitation | Fac. |  |  | ★
Send invitations to eligible students | Coord. |  |  | ★
Track RSVPs and payments | Coord. |  |  | █ | █
Send follow-up to non-responders | Coord. |  |  |  | ★
PHASE 3 — Event Materials
Design formal invitations (HTML + print) | Coord. |  |  | █ | █
Create ceremony program | Coord. |  |  |  | █
Build RSVP and seating materials | Coord. |  |  |  | █
Produce payment tracking log | Coord. |  |  |  | █
Prepare national org. enrollment forms | Coord. |  |  |  |  | ★
PHASE 4 — Logistics
Confirm venue and catering | Coord. |  |  |  | ★
Coordinate faculty RSVP | Coord. |  |  |  | █
Prepare day-of checklist | Coord. |  |  |  |  | █
Submit final headcount to venue | Coord. |  |  |  |  | ★
PHASE 5 — Induction Ceremony
Set up ceremony space | Coord. |  |  |  |  | ★
Manage check-in and fee collection | Coord. |  |  |  |  | ★
Coordinate ceremony with faculty | Coord. |  |  |  |  | ★
Photography and documentation | Coord. |  |  |  |  | █
PHASE 6 — Post-Event Documentation
Submit enrollments to national org. | Coord. | [5 empty] | ★
Update master member database | Coord. | [5 empty] | █
Reconcile payment records | Coord. | [5 empty] | █
Draft post-event summary report | Coord. | [6 empty] | ★
Archive materials per FERPA policy | Coord. | [6 empty] | █
Document process improvements | Coord. | [7 empty] | ★

## 📧 Communications Log
Student Outreach & Communications Log ¦ Spring 2026 Induction Cycle
⚠ SAMPLE DATA — All names and contact info below are fictional. Created for portfolio demonstration only.
Last Name | First Name | Email (Sample) | Grad Year | Invitation Sent | 1st Follow-Up | RSVP Received | Payment Confirmed | Dinner Attending | Notes
Ashworth | Morgan | m.ashworth@university.edu | 2026 | Feb 3 | Feb 10 | Feb 8 | Feb 8 | Yes | Confirmed for ceremony and dinner
Blackwood | Riley | r.blackwood@university.edu | 2026 | Feb 3 |  | Feb 5 | Feb 5 | Yes | Existing member (ceremony attendance only)
Ellsworth | Jamie | j.ellsworth@university.edu | 2026 | Feb 3 | Feb 10 | Feb 11 | Feb 11 | Yes | Paid on receipt of follow-up
Pemberton | Taylor | t.pemberton@university.edu | 2026 | Feb 3 |  | Feb 6 | Feb 4 | Yes | Existing member; already paid...confirmed
Cromwell | Spencer | s.cromwell@university.edu | 2026 | Feb 3 | Feb 10 | Feb 12 | Feb 14 | Yes | Sports conflict...confirmed attending dinner
Merriweather | Quinn | q.merriweather@university.edu | 2027 | Feb 3 |  | Feb 7 | Feb 7 | Yes
Coldwell | Sam | s.coldwell@university.edu | 2027 | Feb 3 | Feb 10 | Feb 14 | Feb 14 | Yes
Fairmont | Drew | d.fairmont@university.edu | 2027 | Feb 3 | Feb 10 | Feb 15 |  | TBD | Payment not yet received as of 2/15
Thornton | Casey | c.thornton@university.edu | 2026 | Feb 3 | Feb 10 |  |  | No | Not eligible; not invited (listed for completeness)
Ravenswood | Jordan | j.ravenswood@university.edu | 2027 | Feb 3 | Feb 10 | Feb 16 | Feb 16 | Yes
Ashbridge | Parker | p.ashbridge@university.edu | 2028 | Feb 3 |  | Feb 6 | Feb 6 | Yes | Enthusiastic response; first induction for this student
Hartwell | Morgan | m.hartwell@university.edu | 2028 | Feb 3 | Feb 10 | Feb 13 | Feb 13 | Yes
Westbrook | Bailey | b.westbrook@university.edu | 2028 | Feb 3 | Feb 10 | Feb 17 | Feb 17 | Yes
Nightingale | Sage | s.nightingale@university.edu | 2028 | Feb 3 |  | Feb 5 | Feb 5 | Yes | Paid same day; very organized
Lakeshore | Avery | a.lakeshore@university.edu | 2027 | Feb 3 | Feb 10 | Feb 18 |  | TBD | ⚠ Follow up needed; no payment
■ Light Sage = RSVP confirmed + payment received
■ Light Gold = RSVP received, payment pending
■ Light Mauve = No RSVP yet — follow-up required
Total Invited: 15 |  | RSVPs Received: 14 |  | Payments Confirmed: 12 |  | Attending Dinner: 12 |  | Pending Follow-Up: 2

## 📊 Outcomes Summary
Spring 2026 Induction Cycle ¦ Outcomes Summary & Post-Event Report
Prepared by: Administrative Coordinator ¦ Audience: Faculty Chapter Advisor ¦ Date: [End of Cycle]
KEY METRICS
Students in English Program (Total) | 34 | Students across 4 program categories (major, ed., double, minor)
Eligible for Induction | 17 | Met all criteria: 3.0+ GPA, sophomore+, 3+ ENGL courses
New Inductees (Spring 2026) | 12 | Successfully inducted at spring ceremony
Existing Members (Returned) | 3 | Returned members attending ceremony; no new fee required
Total Chapter Members (Historical) | 104 | All members since chapter founding, including faculty
Graduating Members (Class of 2026) | 5 | Senior members completing degrees this cycle
Event Deliverables Produced | 6 | Invitations, program, RSVP tracker, payment log, enrollment docs, summary
Payment Discrepancies at Close | 0 | All fees reconciled against enrollment submissions
On-Time Delivery (All Phases) | 100% | All 6 phases completed within planned timeline
Stakeholder Groups Coordinated | 3 | Students, faculty advisors, national Sigma Tau Delta organization
DELIVERABLES PRODUCED
Deliverable | Format | Description
Multi-Tab Eligibility & Tracking Workbook | Excel (.xlsx) | 5-tab workbook with eligibility tracker, planning checklist, Gantt timeline, communications log, and outcomes summary; designed with CLT principles
Formal Induction Invitations | HTML + Print PDF | Branded invitation in institutional navy and gold; dark academia aesthetic; print-ready and email-distributable versions
Honors Induction Ceremony Program | Word / Print PDF | Ceremony order, member list, chapter history, faculty sponsor recognition, national organization statement
RSVP and Payment Tracking Log | Excel | Tracked 4 communication touchpoints per eligible student; flagged pending payments; generated final headcount
National Organization Enrollment Package | Portal + Documents | Submitted all required fields to Sigma Tau Delta national portal; retained confirmation records per institutional policy
Post-Event Summary Report | Word / PDF | Outcomes report for faculty advisor: headcount, financials, process notes, recommendations for next cycle; filed in department records
PROCESS NOTES & RECOMMENDATIONS FOR NEXT CYCLE
What worked well | Building the tracking workbook before outreach began gave every subsequent phase a clean data foundation. The single-source-of-truth design prevented duplicate outreach and payment errors.
Improvement: Timeline | Starting the materials production phase one week earlier would reduce the Week 4 workload. Invitations and ceremony program can be drafted in parallel with the RSVP window, not after it opens.
Improvement: Database | Maintaining a rolling member database between cycles (rather than rebuilding from the registrar pull each spring) would save approximately 3-4 hours of cross-referencing work.
Improvement: Outreach | A templated email suite (initial invitation, follow-up, payment confirmation) would standardize language and reduce drafting time by half.
For the next coordinator | This workbook is designed as a handoff document. Each tab represents one phase of the project. Start with the Eligibility Tracker, work through the Planning Checklist in order, and use the Outcomes tab to close the cycle.
Portfolio Sample ¦ Kayla Canfield ¦ This workbook uses entirely fictional data for demonstration purposes. No real student records are represented.